## David Konekperi
Nr. | Jira ID | Title | Status | Description | Next steps | Date Opened | Last Updated | Planned finished Date | Date completed | Expected duration (in days) | Assigned to
1 | PH-137 | Telegram Chatbot Calculator | Done | Using Keyboard buttons .It Should take inputs from user ad return and return answers .There should be validation | Done | 20/04/2023 | 20/04/2023 | 26/04/2023 | 28/04/2023 | 5 | David K
2 |  | Create telegram Chatbot for AirTime Purchase | Done | A telegram ChatBot to allow user purchase airtime either for self or others | Done | 2023-02-05 | 2023-04-05 | 2023-09-05 | 2023-11-05 | 6 | David K
3 | TCHAT-30 | Telegram Chatbot v2.0 Help Menu | Done | Implementation of Telegram Chatbot v2.0 help menu | Done | 16/05/2023 | 17/05/2023 | 17/04/2023 | 17/05/2023 | 2 | David K
4 | BCM-102 | Implementing Issue Prepaid Card | In progess | Implement Issue Prepaid Cards in Baobab Card Module | In progress | 24/05/2023 | 25/05/2023 | 26/05/2023 |  | 3 | David K
5
6
7
8
9
10
11
12
13 |  |  | I

## Task Distribution
JIRA Ticket | Task | Effort Estimate (Hours) | Comments | Completion Date
BCM-102 | Implement Issue Prepaid Cards | 14 | progress | 26/05/2023
|  | Total Hours: | 14
|  | Total Days: | 2